The Study flow chart to illustrate the three study phases.

Semi-structured Interviews/focus groups with consultants, junior doctors, nursing staff, dieticians, physiotherapists, and therapy assistants (n=20-30).

Review of patients’ clinical records (60)

Identify number of and reasons for referrals to dietetic/nutrition team in the study wards for the last 3 months

Identify the percentage of ONS prescribed in the study wards for the last 3 months.

Phase 1. Baseline practice

*Identifying patients at high risk of poor outcomes

* The nutritional and mobility care provided to inpatients in acute medical wards for older people

Semi-structured interviews/focus groups with patients (n=10-15) and healthcare staff (n=10-20) to assess acceptability of grip strength measurement and adoption.

Regular auditing of the clinical records (the number of patients who have their grip strength measured, the number with low grip strength values, the number of patients who have received the grip strength care plan)

Identify number of and reasons for referrals to dietetic/nutrition team in the study wards for the last 3 months

Identify the percentage of ONS prescribed in the study wards for the last 3 months.

identify implementation costs including the cost of equipment, staff training, notes audit, ONS prescriptions and length of stay.

Phase 3. Monitoring and evaluation of routine grip strength implementation

Monitoring and evaluation of routine grip strength implementation will involve assessing its acceptability, adoption, coverage, and costs.

Phase 2. Training and implementation

* Develop and deliver training programme.

* Start routine implementation of grip strength measurement

Develop a training programme + care plan for managing patients with low grip strength

Train the staff in groups of 2-6 (presentation and practical demonstration) about measuring grip strength and use of the care plan

Routine implementation of grip strength measurement; measure grip strength for newly admitted patients in the study wards + use care plan for patients with low grip strength